| INPUT | OUTPUT | OUTCOMES |
| --- | --- | --- |
| Resources (Who and what will contribute to the strategy) | Strategy (What we are going to do) | Participants (Who will be the ones participating in the strategy) | Short-Term (Attitude, Knowledge, or Skill we want to change) | Intermediate (Behavior we want to change) | Long-Term Outcome ( Condition we want to change) |

| INPUT | OUTPUT | OUTCOMES |
| --- | --- | --- |
| Resources (Who and what will contribute to the strategy) | Strategy (What we are going to do) | Participants (Who will be the ones participating in the strategy) | Short-Term (Attitude or Knowledge we want to change) | Intermediate (Behavior we want to change) | Long-Term Outcome ( Condition we want to change) |
| Library – computer lab Community College – instructor - tech students Chamber of Commerce - advertisement | Conduct a five week web design course Provide follow-up technical assistance. | Small business owners in the region | Attitude: A website would be an important tool for my business Knowledge: What information is needed to build a web site Skill: How to build a website OR How to develop a plan to work with a web designer to build a site. | Participants launch a website for their small businesses. | Small businesses with new websites: Increase revenue Increase jobs |

Strategy:

| Step to Accomplish | Responsibility (Who is taking responsibility for completing step?) | Key Contact (If Team responsibility) | Goal Date (Anticipated completion date) | Completion Date (fill in when completed) |
| --- | --- | --- | --- | --- |

Strategy:  Implement a six session e-commerce workshop for small businesses and entrepreneurs by December 2011.

| Step to Accomplish | Responsibility (Who is taking responsibility for completing step?) | Key Contact (If Team responsibility) | Goal Date (Anticipated completion date) | Completion Date (fill in when completed) |
| --- | --- | --- | --- | --- |
| Work with the Chamber of Commerce and Small Business Development Center to identify small businesses in the region. | Jim, Shirley, & Bob | Bob | Nov. 2010 |  |
| Develop a survey for use with existing small businesses to identify current web use status and access. | Ann, Sue, & Albert | Sue | Dec. 2010 |  |
| Identify potential curricula and trainers | Robert, Alice, Sam | Alice | Dec. 2010 |  |
| Conduct survey – Each partner will conduct at least 10 surveys one-on-one with identified businesses. | All | Jim | Jan. 2011 |  |
| Analyze surveys | Jim, Albert, Sue | Jim | Feb. 2011 |  |
| Explore matches between identified needs (from surveys) and existing e-commerce curricula available through Extension Service, Community College Resource Center, & Small Business Center. | Robert, Alice, Sam | Alice | March 2011 |  |
| Finalize content of training series | Robert, Alice, Sam | Alice | April 2011 |  |
| Recruit instructors | Robert | Robert | April 2011 |  |
| Develop brochure outlining training content and dates. | Shirley, Alice, Robert | Shirley | May 2011 |  |
| Host kick-off breakfast to showcase series | All | Albert | June, 2011 |  |
| Conduct training series | Trainers | Robert | August. 2011 |  |
| Conduct site visits to gauge adoption and provide technical assistance | Bob, Jim, Trainers | Jim | Oct. 2011 |  |

# Text boxes

STRONGER ECONOMIES TOGETHER (SET) WORKBOOK

MODULE EIGHT:  Planning for Success

Worksheet 1				 Regional Economic Development Planning Chart    		       Slide11, 17, 22

STRONGER ECONOMIES TOGETHER (SET) WORKBOOK

MODULE EIGHT: Planning for Success

Worksheet 2			 Regional Economic Development Planning Chart - Example    		               Slide 11

STRONGER ECONOMIES TOGETHER (SET) WORKBOOK

MODULE EIGHT: Planning for Success

Worksheet 3						 Plan of Work				                         Slide 34

STRONGER ECONOMIES TOGETHER (SET) WORKBOOK

MODULE EIGHT: Planning for Success

Worksheet 4				      Plan of Work - Example			                         Slide 34