| Summary of Key Activities | By When? |
| --- | --- |
| Distribute SET application form (draft) | March 7 |
| Add state contacts to SET application form | March 12 |
| Finalize State Partner Team | March 21 |
| Application period Opens | March 26 |
| Finalize State Training Team & submit names to Rachel Welborn/SRDC. Identify Extension contact who will complete IRB requirements | March 31 |
| Finalize communications plan & submit to Suzette Agans | March 31 |
| Implement communications plan (inc. media releases) | March-April |
| Applications due to State Partner Team | May 4 |
| State Partner Team submits reviews and top 4 proposals to Suzette Agans | May 18 |
| State Training Team attends National Workshop | June 11-13 |
| SET regions selected | Approx. June 30 |
| Meet with each regional team to finalize details | July-August |
| Participate in monthly calls of SET Phase III states | July , then monthly |
| Launch SET (including securing IRB approval) | Fall |